## 330 Process
330 Process Checklist
|  | Complete | N/A
RFQ Stage
· RFQ has been drafted by the PM and reviewed by DoP
· PM or DoP has sent the RFQ to CA
· RFQ has been posted on OFCC Ohio Register web page (State funded projects take 1 week to post)
· CA has recorded an appointment on their calendar of 330 submittal due date and included the PM, DoP, and front desk attendant on the appointment
· 330s received and stamped at front desk
· Front desk attendant has distributed all copies to CA
· CA maintains one 330 copy and gives remaining copies to PM
· Front desk gives the CD to Data Control Technician
· Data Control Technician has uploaded and saved the CD in the appropriate electronic file
Scoring Stage
· CA has completed the information on the Summary tab (green highlights)
· CA has inserted values for Section 2 from the RFQ score sheet in Summary tab
· CA has scored Section 1 on the Summary tab
· CA has saved the document in project electronic file and notified PM
· PM has completed the remainder of the score sheet and saved it in the electronic project file (0100_Procure_Products-Services)
· PM notifies project controls for project to be placed on the 330 mtg. Agenda
· PM has reviewed the 330s scores at the weekly 330 meeting and brings the shortlist memo with them to the meeting for approval.
· PM has saved the final score sheet as a PDF in the electronic project file and marked it as FINAL. (0100_Procure_Products-Services)
Shortlist Stage
· CA begins filling in the Shortlist Approval Memo
· CA has recorded all 330s received in a timely manner on the form
· CA has returned any 330s received late back to the vendor
· PM has completed the Shortlist Approval Memo and it has been initialed by the DoP
· The PM takes the Shortlist Approval Memo with them to the 330 meeting for approval by the University Architect and Associate Vice President (DB and CMR require additional approvals)
· PM has provided the approved memo with interview information to CA
· CA has notified the shortlisted and not shortlisted firms
· The PM has scheduled the interview date and time and invited the the selection committee to attend.

## Summary
Design Build 330 Score Summary Sheet
[PM NAME]
[PROJECT NUMBER]
[PROJECT NAME]
| Design Build 330 Submittal | Construction Cost: | $$$$$
| (received date) | Total Project Cost: | $$$$$ | 1. Primary Firm Location and Workload |  | 2. Primary Qualifications |  |  |  | 3. Key Consultant Qualifications |  | 4. Overall Team Qualifications |  |  |  | 5. Overall Team Experience
| Project Description here |  |  | Proximity of Firm to Project Site | Amount of Contracts awarded by Contracting Authority in previous 24 months | Project Management Lead | Project Design Lead | Technical Staff | Construction Administration Staff | Key Consultants | Proposed EDGE-certified Consultant Participation | Previous Team Collaboration | LEED Registered / Certified Project Experience | BIM Project Experience | Team Organization | Previous Team Performance | Experience with Similar Projects / Delivery Methods | Budget and Schedule Management | Knowledge of Ohio Capital Improvements Process
Totals
| Firm Name | EDGE Vendor | Other Consultants | 1a | 1b | 2a | 2b | 2c | 2d | 3a | 3b | 4a | 4b | 4c | 4d | 5a | 5b | 5c | 5d
|  |  |  | 5 | 5 | 10 | 0 | 0 | 0 | 10 | 5 | 3 | 2 | 3 | 2 | 10 | 10 | 5 | 5
0 | Firm 1 | [18 empty] | 0
0 | Firm 2 | [18 empty] | 0
0 | Firm 3 | [18 empty] | 0
0 | Firm 4 | [18 empty] | 0
0 | Firm 5 | [18 empty] | 0
0 | Firm 6 | [18 empty] | 0
0 | Firm 7 | [18 empty] | 0
0 | Firm 8 | [18 empty] | 0
0 | Firm 9 | [18 empty] | 0
0 | Firm 10 | [18 empty] | 0
0 | Firm 11 | [18 empty] | 0
0 | Firm 12 | [18 empty] | 0
0 | Firm 13 | [18 empty] | 0
0 | Firm 14 | [18 empty] | 0
0 | Firm 15 | [18 empty] | 0
0 | Firm 16 | [18 empty] | 0
0 | Firm 17 | [18 empty] | 0
0 | Firm 18 | [18 empty] | 0
0 | Firm 19 | [18 empty] | 0
0 | Firm 20 | [18 empty] | 0
0 | Firm 21 | [18 empty] | 0
0 | Firm 22 | [18 empty] | 0
0 | Firm 23 | [18 empty] | 0
0 | Firm 24 | [18 empty] | 0
0 | Firm 25 | [18 empty] | 0
0 | Firm 26 | [18 empty] | 0
0 | Firm 27 | [18 empty] | 0
0 | Firm 28 | [18 empty] | 0
Note on H11: Experience/ability of Project Manager to manage scope/budget/schedule/quality
Note on I11: Experience / creativity of project designer to achieve owner's vision and requirements
Note on J11: Experience / ability of technical staff to coordinate construction documents and develop accurate estimates and schedules
Note on K11: Experience / ability of field representatives to identify and solve issues during construction
Note on L11: Experience / ability of key consultants to perform effectively and collaboratively
Note on N11: Projects that a majority of the team members have worked together
Note on Q11: Clarity of responsibility / communication demonstrated by table of organization
Note on R11: Past performance as indicated by evaluations and letters of reference
Note on T11: Performance in completing projects within original construction budget and schedule
Note on C13: Insert Name of EDGE vendor or vendors (if applicable)
Note on G13: Score based on Contract Value Report in Netlink.
Note on H13: Utilize the resumes and 330 projects submited, any personal knowledge you have, other PMs, and evaluations in the FDC SHARE folder.
Note on I13: Utilize the resumes and 330 projects submited, any personal knowledge you have, other PMs, and evaluations in the FDC SHARE folder.
Note on J13: Utilize the resumes and 330 projects submited, any personal knowledge you have, other PMs, and evaluations in the FDC SHARE folder.
Note on K13: Utilize the resumes and 330 projects submited, any personal knowledge you have, other PMs, and evaluations in the FDC SHARE folder.
Note on L13: Key consultants can be members of the primary team and should scored accordingly.
Note on M13: This score is based on a maximum of 5 point. -There is one (1) point earned for each 2% above the 5% for PRECONSTRUCTION ONLY - If a firm is 100% EDGE they receive a ZERO. They are only eligible to receive points if they sub-contract their work to another EDGE firm to earn points beyond the 5%.
Note on N13: Refer to the matrix provided in the 330. Weighting should be based on quality of team - including consultant representation.
Note on O13: If a firm only provides 10 projects, score them based on these projects. If a firm provides additional information in Section H, it may be taken into account.
Note on P13: If the project is not using BIM, the PM should delete this section from the RFQ prior to posting, and leave this section unscored. If the project is using BIM, refer to the 330 and score accordingly.
Note on Q13: Refer to the organizational chart for the entire team. This includes all of the primary and secondary consultants.
Note on R13: Refer to the FDC SHARE drive evaluations. Consider contacting other PMs. Contact references. The PM must document if negative. Use personal experience.
Note on S13: Refer to the matrix provided in the 330. Ensure the matrix aligns with what you posted in the RFQ. Ensure that all ten projects meet the criteria and quality listed.
Note on T13: Use Information contained within the 330, personal knowledge, and evaluations on the FDC SHARE drive.
Note on U13: Use Information contained within the 330, personal knowledge, and evaluations on the FDC SHARE drive.
Note on I14: Please refer to the RFQ and use the numbers from your score sheet in 2b, 2c, and 2d.