## Budget Template Instructions
Instructions to complete a Project Budget
This template is a tool to help develop a Total Project Cost. Each project will have unique circumstances and the default settings should be adjusted accordingly. To improve functionality macros have been included. Cells highlighted in green require review and/or modification. All other cells should remain unchanged to ensure the Total Customer Expense is valid, as they are generated through a series of formulas and look-up tables.
Rules of the Road
1 | Project Budget cells are color coded.
Green = Review and/or Modify
2 | Spreadsheet tabs are color coded:
Red = Budget Instructions
Orange = Project Budget Development
Green = PDF Print Out for Customer and e-Builder Budget Match
Purple = Reference tabs
Where to begin:
1 | Begin on the Estimate Template tab
a. Enter project information
b. Complete the applicable section depending on project size and available detail
1. Small Project - Under $250k (see note below for projects over $200k)
2. Capital Project - Over $200k (Note: Capital plan threshold is not the same as the $250k state threshold - for now, if over $200K has to go on capital plan, but you can fill out the Small Project estimate for budgeting)
c. Adjust green boxes as appropriate
2 | Below the Line for OSU Wexner Medical Center projects; these budget lines will be the Plan Phase used in Workday to issue POs against the project
3 | Total Project Estimate (PDF ME).
a. (1) Click Sort & Filter"
b. (2) Click "Reapply"
c. Print page as PDF
4 | Funding Increase Worksheet
a. Use this sheet if a funding increase is required/requested. This will help recalcualte fee, contingency, and total cost.
Tab Definitions
| Estimate Template | Captures and Calculates Projects Costs
| Below the Line | Non-project Budget Costs Customers May Also Be Budgeting
| Total Project Estimate (PDF ME) | Printout For Customer
| Funding Increase Worksheet | Aid to determine cost impact to project when additional funds may be required
| Basic Services Fees | A/E Basic Services Fees Table
| Fee Look Up Table | Backup Information on CMR, DB, Cx, etc. Fees
| Benchmark Cost | Backup Information on Cost Per Square Feet by Space Type
| Consultants | Backup Information Consultants to Consider for a Project
Facilities Operations and Development
Design and Construction
400 Central Classroom Building
2009 Millikin Road
Columbus, OH 43210
Phone (614) 292-4458
Fax (614) 292-2539
http://fod.osu.edu

## Estimate Template
Estimate Template for All Projects
OSU-######
Project Name
Scope
Gross Square Feet
Expand / Collapse |  |  | Small Project Estimate
| Type of PO | Purchase Order |  |  |  | Detailed Estimate Module
| Contractor | TBD
| A/E | N/A
| Construction | [5 empty] | 0
| Labor and Material |  |  |  |  | 0 | <- This Cell can be overwritten
| Permit |  |  |  |  | 0
| Asset Tag | None |  |  |  | 0
| Other |  |  |  |  | 0
| Other |  |  |  |  | 0
| Other |  |  |  |  | 0
| Fee |  |  |  | 11% | 0
| Technology |  |  |  |  | 0
| FFE | [5 empty] | 0
| 03-0310 | Furniture |  |  |  | 0
| 03-0320 | Equipment |  |  |  | 0
| 03-0330 | Project Coordination |  |  |  | 0
| 03-0340 | Medical Equipment |  |  |  | 0
| 03-0340 | Signage |  |  |  | 0
| Move | [5 empty] | 0
| 06-0640 | Moving |  | 0 | None | 0
| Design Fee | [5 empty] | 0
| Criteria A/E | Contracted |  |  | 0% | 0
| A/E |  |  |  | 0% | 0
| Reimbursables |  |  |  | 0% | 0
| Additional Services |  |  |  | 0% | 0
| Contingency | [5 empty] | 0
[5 empty] | 10% | 0
| Local Admin Fee | [5 empty] | 0
[5 empty] | 2% | 0
| Project Budget | [5 empty] | 0 | RED TEXT INDICATES ESTIMATE IS OVER $250K THRESHOLD
BLUE TEXT INDICATES ESTIMATE IS OVER $200K CAPITAL PLAN THRESHOLD
Alternates
|  | Description | Construction | Design | Contingency | Fee | Total
| Alternate 1 |  | 0 | 0 | 0 | 0 | 0
| Alternate 2 |  | 0 | 0 | 0 | 0 | 0
| Alternate 3 |  | 0 | 0 | 0 | 0 | 0
| Alternate 4 |  | 0 | 0 | 0 | 0 | 0
| Alternate 5 |  | 0 | 0 | 0 | 0 | 0
| Alternate 6 |  | 0 | 0 | 0 | 0 | 0
| Alternate 7 |  | 0 | 0 | 0 | 0 | 0
| Alternate 8 |  | 0 | 0 | 0 | 0 | 0
| Alternate 9 |  | 0 | 0 | 0 | 0 | 0
| Alternate 10 |  | 0 | 0 | 0 | 0 | 0
| Alternate 11 |  | 0 | 0 | 0 | 0 | 0
| Alternate 12 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
Expand / Collapse |  |  | Capital Project
| Project Type |  | Renovation |  | Total Project Cost | 0
| Complexity Type |  | Average
| Delivery Type |  | General Contractor
| State Funding Amount |  | 0
| 02 | Construction |  |  |  |  | 0
| 02-0210 | Construction
|  | Type of Space | Percent | Difficulty | Premium | Cost / ft2 | Sub-Total by Type
|  | General Classroom | 100% | Med | 1 | 161.975 | 0
|  | General Classroom | 0% | Med | 1 | 0 | 0
|  | General Classroom | 0% | Med | 1 | 0 | 0
Enter My Own Construction Cost
0
Modifiers
|  | Asbestos/Haz Mat | Unsuitable Soils | Premium Landscape | Premium Site Work | Limit Time / Site
|  | 10% | 0% | 0% | 0% | 0% | 0
Asset Tagging
| 0 | None |  |  |  |  | 0
General Classroom
|  | Additional Item | Description |  |  | 0 | 0
|  | Additional Item | Description |  |  | 0 | 0
Escalation
|  | Years Applied | Rate | Factor
|  | 1 | 5% | 1.05 |  | 0 | 0
| Technology |  |  | None | 0% |  | 0
| Labor and Materials | [5 empty] | 0
| General Conditions |  |  |  | 10% |  | 0
| Construction Stage Personnel Cost (CMR or DB Only) |  |  | None | 0% |  | 0
| Contractor's Contingency |  |  |  | 0% |  | 0
| AoR Construction Stage Design Fee (DB Only) |  |  |  | 0% |  | 0
| Fee (CMR or DB Only) |  |  |  | 0% |  | 0
| 02-0230 | Civic Structure* ( not included in ConstructionTotal, but included in Total Project Cost) |  |  | 0% |  | 0 | *Civic Structure cost is not included in ConstructionTotal, but added into Total Project Cost.
| 03 | FFE |  |  |  |  | 0
| 03-0310 | Furniture |  | None | 0% |  | 0
| 03-0320 | Equipment |  | None | 0% |  | 0
| 03-0330 | Project Coordination |  | None | 0% |  | 0
| 03-0340 | Medical Equipment |  | None | 0% |  | 0
| 03-0340 | Signage |  | None | 0% |  | 0
| 01 | Professional Services |  |  |  |  | 0
| 01-0110 | Design Budget | 0 |  |  |  | 0
|  | Basic A/E Services |  |  | 0% |  | 0
|  | Reimbursables |  | Low | 1% |  | 0
|  | Additional Services |  | Low | 1% |  | 0
|  | LEED Certification |  | No | - - |  | 0
| 01-0120 | Precon (DB & CMR) |  |  |  |  | 0
|  | Preconstuction Compensation |  |  | 0% |  | 0
|  | AoR Design Services Compensation |  |  | 0% |  | 0
|  | AoR Reimbursables |  | Low | 0% |  | 0
|  | AoR Additional Services |  | Low | 0% |  | 0
|  | AoR LEED |  | No | - - |  | 0
| 01-0130 | Commissioning |  | Renovation | 1.689% |  | 0
| 01-0140 | Consulting Services |  |  |  |  | 0
| 01-0150 | In-House Design |  |  |  |  | 0
| 01-0160 | Planning |  |  |  |  | 0
| 01-0170 | Study |  |  |  |  | 0
| 04 | Art |  |  |  |  | 0
| 04-0410 | Percent for Art |  |  | 0% |  | 0
| 05 | Capital Planning Savings |  |  |  |  | 0
| 05-0510 | Capital Planning Savings |  |  |  |  | 0
| 06 | Project Administration |  |  |  |  | 0
| 06-0610 | Local Admin Fee |  |  | Fixed |  | 0
| 06-0620 | PMO |  |  |  |  | 0
| 06-0630 | Legal |  |  |  |  | 0
| 06-0640 | Advertising |  |  |  |  | 0
| 06-0650 | Moves |  | None | 0 |  | 0
| 06-0690 | Misc (General Expenditures) | Previously part of Contingency (Project/Construction) |  | 1% |  | 0 | The Total Contingency Budgeted is | 10%
| 09 | Contingency |  |  |  |  | 0 | Adjust the percentages for Misc (General Expenditures), Project Contingency, Construction Contingency, Risk Contingency to add up to the expected Total Contingency amount.
| 09-0910 | Project Contingency |  |  | 2% |  | 0
| 09-0920 | Construction Contingency | Typically 4% - 7% |  | 7% |  | 0
| 09-0930 | Risk Contingency |  |  | 0% |  | 0
|  | Below the Line |  |  |  |  | 0
Expand / Collapse |  |  | Detailed Estimate
Base Bid
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Alternates
Alternate 1
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Additional Alternates
Alternate 2
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Additional Alternates
Alternate 3
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Additional Alternates
Alternate 4
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Additional Alternates
Alternate 5
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | No Additional Alternates
Alternate 6
|  | Drywall Partition | 0 | SF | 7 | 0
|  | Painting | 0 | SF | 0.75 | 0
|  | Door | 0 | EA | 775 | 0
|  | Hardware | 0 | EA | 775 | 0
|  | Ceramic Wall Tile | 0 | SF | 9 | 0
|  | Carpet Tile | 0 | SF | 10 | 0
|  | VCT | 0 | SF | 2 | 0
|  | LVT | 0 | SF | 7.5 | 0
|  | Toilet Install | 0 | EA | 7000 | 0
|  | Restroom Sink Install | 0 | EA | 1000 | 0
|  | Sprinkler Addition (Heads and Branches) | 0 | SF | 1.5 | 0
|  | Outlets | 0 | EA | 500 | 0
|  | Replace Lights | 0 | SF | 3 | 0
|  | Fire Alarm Install | 0 | EA | 7000 | 0
|  | VAV | 0 | EA | 7000 | 0
|  | Package Unit 10 ton | 0 | EA | 21000 | 0
|  | General Requirements | 1 | % | 10% | 0
[6 empty] | 0 | Done
Note on C132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Expected costs during construction for PO work: Wireless Access Points, Public Safety, Construction Cameras, etc

## Below The Line
RENOV######
Project Name
Fund:___________ Org: ________ Acct: ________
Construction
| Original Estimate | Change | Change | Change
FOD Estimate | 0 |  |  |  | 0
General Trades |  |  |  |  | 0
Mechanical |  |  |  |  | 0
Electrical |  |  |  |  | 0
Plumbing |  |  |  |  | 0
Permitting Fees |  |  |  |  | 0
Other |  |  |  |  | 0
Cost of Construction |  |  |  |  | 0
Contingency (default 10%) | 0 | 0 | 0 | 0 | 0
| Total Construction Cost (TCC) |  |  |  | 0
Fixtures, Furniture & Equipment
Fixtures |  |  |  |  | 0
Furniture |  |  |  |  | 0
Clinical Engineering |  |  |  |  | 0
Minor Equipment |  |  |  |  | 0
Major Moveable Equipment |  |  |  |  | 0
Artwork |  |  |  |  | 0
Other |  |  |  |  | 0
Cost of FF&E |  |  |  |  | 0
Contingency (default 10%) | 0 | 0 | 0 | 0 | 0
| Total FF&E Costs |  |  |  | 0
Moves & Storage
Moves |  |  |  |  | 0
Storage |  |  |  |  | 0
Other |  |  |  |  | 0
Cost of Moves & Storage |  |  |  |  | 0
Contingency (default 10%) | 0 | 0 | 0 | 0 | 0
| Total Moves & Storage Costs |  |  |  | 0
Information Technology
Devices (Phones, Computers, Printer, etc) |  |  |  |  | 0
Servers / Switches |  |  |  |  | 0
Infrastructure / Wireless |  |  |  |  | 0
AV / Digital Display |  |  |  |  | 0
Other |  |  |  |  | 0
Cost of Information Technology |  |  |  |  | 0
Contingency (default 10%) | 0 | 0 | 0 | 0 | 0
| Total IT Costs |  |  |  | 0
Other
Security |  |  |  |  | 0
Signage |  |  |  |  | 0
ADA |  |  |  |  | 0
Consultant |  |  |  |  | 0
Other |  |  |  |  | 0
Cost of Other Items |  |  |  |  | 0
Contingency (default 10%) | 0 | 0 | 0 | 0 | 0
| Total Other Costs |  |  |  | 0
| Total Project Estimate |  |  |  | 0
Capital Funds
Non Capital Funds
College of Medicine Funds

## Total Project Estimate (PDF ME)
OSU-######
Project Name
Purchase Order |  |  |  |  | 2024
01 | Professional Services |  |  |  | 0
01-0110 | Design Budget | 0% |  | 0 | 0
| Basic A/E Services | 0% | 0 |  | 0
| Reimbursables | 1% | 0 |  | 0
| Additional Services | 1% | 0 |  | 0
| LEED Certification | - - | 0 |  | 0
01-0120 | Precon CM@R | 0% |  | 0 | 0
| Preconstuction Compensation | 0% | 0 |  | 0
| AoR Design Services Compensation | 0% | 0 |  | 0
| AoR Reimbursables | 0% | 0 |  | 0
| AoR Additional Services | 0% | 0 |  | 0
| AoR LEED | - - | 0 |  | 0
01-0130 | Commissioning |  |  | 0 | 0
01-0140 | Consulting Services |  |  | 0 | 0
01-0150 | In-House Design |  |  | 0 | 0
01-0160 | Planning |  |  | 0 | 0
01-0170 | Study |  |  | 0 | 0
02 | Construction |  |  |  | 0
02-0210 | Construction Activities |  |  | 0 | 0
| Labor and Material |  | 0 |  | 0
| Permit |  | 0 |  | 0
| Asset Tag |  | 0 |  | 0
| Other |  | 0 |  | 0
| Other |  | 0 |  | 0
| Other |  | 0 |  | 0
| Fee |  | 0 |  | 0
| Technology |  | 0 |  | 0
02-0220 | Contractor's Contingency (CMR or DB) |  |  | 0 | 0
| Civic Structure1. |  |  |  | 0
03 | FFE |  |  |  | 0
03-0310 | Furniture |  |  | 0 | 0
03-0320 | Equipment |  |  | 0 | 0
03-0330 | Project Coordination |  |  | 0 | 0
03-0340 | Medical Equipment |  |  | 0 | 0
03-0350 | Signage |  |  | 0 | 0
04 | Art2. |  |  |  | 0
05 | Capital Planning Savings |  |  |  | 0
06 | Project Administration |  |  |  | 0
06-0610 | Local Admin Fee |  |  | 0 | 0
06-0620 | PMO |  |  | 0 | 0
06-0630 | Legal |  |  | 0 | 0
06-0640 | Advertising |  |  | 0 | 0
06-0650 | Moves |  |  | 0 | 0
06-0690 | Misc (General Expenditures) |  |  | 0 | 0
09 | Contingency |  |  |  | 0
09-0910 | Project Contingency |  |  | 0 | 0
09-0920 | Construction Contingency |  |  | 0 | 0
09-0930 | Risk Contingency |  |  | 0 | 0
| Alternates |  |  |  | 0
Alternate 1 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 2 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 3 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 4 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 5 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 6 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 7 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 8 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 9 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 10 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 11 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
Alternate 12 |  |  |  | 0 | 0
Construction | 0 |  |  |  | 0
Design | 0 |  |  | 0 | 0
Contingency | 0 |  |  | 0 | 0
Fee | 0 |  |  | 0 | 0
| Below The Line Costs3. |  |  |  | 0
|  |  | Total Project Cost (FOD) |  | 0
|  |  | Total Project Cost with Alternates (FOD) |  | 0
|  |  | Total Customer Expense |  | 0
* Budget estimate is non-binding and may be updated as project progresses 1. If total cost is $4M+, Civic Structure is included at 2% of construction budget 2. If State Capital Funds equal $4M+, Art funding is included at 1% of the State Capital Funding amount 3. Below the Line Costs are customer expenses outside of the scope of work managed by FOD and the FOD Project Cost

## Funding Increase Worksheet
OSU-######
Project Name
|  | ORIGINAL | INCREASE | FINAL
01 | Professional Sevices | 0 | 0 | 0
01-0110 | Design
| Basic A/E Services | 0 | 0 | 0
| Reimbursables | 0 | 0 | 0
| Additional Services | 0 | 0 | 0
| LEED Certification | 0 | 0 | 0
01-0120 | Precon (DB & CMR)
| Preconstuction Compensation | 0 | 0 | 0
| AoR Design Services Compensation | 0 | 0 | 0
| AoR Reimbursables | 0 | 0 | 0
| AoR Additional Services | 0 | 0 | 0
| AoR LEED | 0 | 0 | 0
01-0130 | Commissioning | 0 | 0 | 0
01-0140 | Consulting Services | 0 | 0 | 0
01-0150 | In-House Design | 0 | 0 | 0
01-0160 | Planning | 0 | 0 | 0
01-0170 | Study | 0 | 0 | 0
02 | Construction | 0 | 0 | 0
02-0210 | Construction Activities | 0 | 0 | 0
| Labor and Material | 0 | 0 | 0
| Fee | 0 | 0 | 0
| Technology | 0 | 0 | 0
| Permit | 0 | 0 | 0
| Other | 0 | 0 | 0
| Other | 0 | 0 | 0
| Other | 0 | 0 | 0
02-0220 | Contractor's Contingency (CMR or DB) | 0 | 0 | 0
02-0230 | Civic Structure1. | 0 | 0 | 0
03 | FFE | 0 | 0 | 0
03-0310 | Furniture | 0 | 0 | 0
03-0320 | Equipment | 0 | 0 | 0
03-0330 | Project Coordination | 0 | 0 | 0
03-0340 | Medical Equipment | 0 | 0 | 0
04 | Art | 0 | 0 | 0
05 | Capital Planning Savings | 0 | 0 | 0
06 | Project Administration | 0 | 0 | 0
06-0610 | Local Admin Fee | 0 | 0 | 0
06-0620 | PMO | 0 | 0 | 0
06-0630 | Legal | 0 | 0 | 0
06-0640 | Advertising | 0 | 0 | 0
06-0650 | Moves | 0 | 0 | 0
06-0690 | General Expenditures | 0 | 0 | 0
09 | Contingency | 0 | 0 | 0
09-0910 | Project Contingency | 0 | 0 | 0
09-0920 | Construction Contingency | 0 | 0 | 0
09-0930 | Risk Contingency | 0 | 0 | 0
| Below The Line Costs3. | 0 | 0 | 0
Fixed
| Total FOD Project Cost | 0 | 0 | 0
| Total Customer Expense | 0 | 0 | 0

## ConceptualConstructionEstimate (hidden)
#REF!
Project Name
Customer
Address
City
Modifiers
| Type of Project | New Construction | New Construction
| Square Feet (5,000+ SF) | 0 |  |  | Asbestos/Haz Mat
| Number of Parking Spaces | 0 | Parking Lot |  | 1
Unsuitable Soils
| Type of Space | General Classroom | Office | Mechanical Space | 1
| Percent | 100% | 0% | 0% | Premium Landscaping
| Difficulty Level | New | New | New | 1
| Cost per | 316.635 | 0 | 0 | Premium Site Work
| Sub-Total by Type | 0 | 0 | 0 | 1
Constraints on Time or Site
| Total Modified Cost per ft2 |  | 0 |  | 1
|  | Total Cost per Parking Space | 0
| Additional Item |  | 0
| Additional Item |  | 0
| Conceptual Project Budget |  | Cost per Square Foot | Cost per Parking Space | Total Cost
| Cost of Construction |  | 0 | 0 | 0
| Soft Cost Allocation |  | 40% |  | 0
| Below the Line Costs |  | 15% |  | 0
| Civic Structure | 1 | 0% |  | 0
| Current Year Customer Expense |  |  |  | 0
| Estimated years to starting date of construction: |  | 0 | years
| Percentage Inflation Rate per annum is: |  | 3%
| Total Inflation Factor with compounding: |  | 1
| Civic Structure |  | 0%
| Customer Expense with Inflation |  |  |  | 0

## Basic Services Fees
Chart of Basic Services Fees - July 1, 2007
Type A Project: Buildings of average complexity w/o any extensive mechanical/electrical systems,
structural, or design criteria. Examples: classrooms, admin offices, dorms
Type B Project: Difficult buildings of specialized architectural character or requiring special study
or analysis. Examples: research labs, libraries, health care facilities, theatres,
museums, sports complexes, student unions
Type C Project: Buildings of an historical, memorial, or monumental nature
Examples: Historical restoration, memorial facilities, individual custom residential
| ¦---------------- | Percentage Fees by Type of Project Complexity |  |  |  | ----------------¦
(Pct values appearing in more than one cost range are shown in italics.)
Const Cost | A-Average |  | B-Difficult |  | C-Hist/Memorial
at least
($1000's) | New Const | Renov | New Const | Renov | New Const | Renov
0 | 0% | 0% | 0% | 0% | 0% | 0%
0.001 | 12% | 14.4% | 13% | 15.6% | 14% | 16.8%
1 | 12% | 14.4% | 13% | 15.6% | 14% | 16.8%
50 | 10% | 12% | 11% | 13.2% | 12% | 14.4%
75 | 9.5% | 11.4% | 10.5% | 12.6% | 11.5% | 13.8%
100 | 9.2% | 11.04% | 10.2% | 12.24% | 11.2% | 13.44%
200 | 8.9% | 10.68% | 9.9% | 11.88% | 10.9% | 13.08%
300 | 8.6% | 10.32% | 9.6% | 11.52% | 10.5% | 12.6%
400 | 8.3% | 9.96% | 9.3% | 11.16% | 10.3% | 12.36%
500 | 8% | 9.6% | 9% | 10.8% | 10% | 12%
600 | 7.8% | 9.36% | 8.8% | 10.56% | 9.8% | 11.76%
700 | 7.6% | 9.12% | 8.6% | 10.32% | 9.6% | 11.52%
800 | 7.4% | 8.88% | 8.4% | 10.08% | 9.4% | 11.28%
900 | 7.2% | 8.64% | 8.2% | 9.84% | 9.2% | 11.04%
1000 | 6.9% | 8.28% | 7.9% | 9.48% | 8.9% | 10.68%
1100 | 6.86% | 8.23% | 7.86% | 9.43% | 8.86% | 10.63%
1200 | 6.82% | 8.18% | 7.82% | 9.38% | 8.82% | 10.58%
1300 | 6.78% | 8.14% | 7.78% | 9.34% | 8.78% | 10.54%
1400 | 6.74% | 8.09% | 7.74% | 9.29% | 8.75% | 10.5%
1500 | 6.7% | 8.04% | 7.7% | 9.24% | 8.74% | 10.49%
1600 | 6.66% | 7.99% | 7.66% | 9.19% | 8.7% | 10.44%
1700 | 6.62% | 7.94% | 7.62% | 9.14% | 8.66% | 10.39%
1800 | 6.58% | 7.9% | 7.58% | 9.1% | 8.62% | 10.34%
1900 | 6.54% | 7.85% | 7.54% | 9.05% | 8.58% | 10.3%
2000 | 6.5% | 7.8% | 7.5% | 9% | 8.54% | 10.25%
2100 | 6.48% | 7.78% | 7.48% | 8.98% | 8.5% | 10.2%
2200 | 6.46% | 7.75% | 7.46% | 8.95% | 8.48% | 10.18%
2300 | 6.42% | 7.7% | 7.42% | 8.9% | 8.46% | 10.15%
2400 | 6.4% | 7.68% | 7.4% | 8.88% | 8.42% | 10.1%
2500 | 6.38% | 7.66% | 7.38% | 8.86% | 8.4% | 10.08%
2600 | 6.36% | 7.63% | 7.36% | 8.83% | 8.38% | 10.06%
2700 | 6.34% | 7.61% | 7.34% | 8.81% | 8.36% | 10.03%
2800 | 6.32% | 7.58% | 7.32% | 8.78% | 8.34% | 10.01%
2900 | 6.3% | 7.56% | 7.3% | 8.76% | 8.3% | 9.96%
3000 | 6.28% | 7.54% | 7.28% | 8.74% | 8.28% | 9.94%
3100 | 6.26% | 7.51% | 7.26% | 8.71% | 8.26% | 9.91%
3200 | 6.24% | 7.49% | 7.24% | 8.69% | 8.24% | 9.89%
3300 | 6.22% | 7.46% | 7.22% | 8.66% | 8.22% | 9.86%
3400 | 6.2% | 7.44% | 7.2% | 8.64% | 8.2% | 9.84%
3500 | 6.19% | 7.43% | 7.19% | 8.63% | 8.19% | 9.83%
3600 | 6.18% | 7.42% | 7.18% | 8.62% | 8.18% | 9.82%
3700 | 6.17% | 7.4% | 7.17% | 8.6% | 8.17% | 9.8%
3800 | 6.16% | 7.39% | 7.16% | 8.59% | 8.16% | 9.79%
3900 | 6.15% | 7.38% | 7.15% | 8.58% | 8.15% | 9.78%
4000 | 6.14% | 7.37% | 7.14% | 8.57% | 8.14% | 9.77%
4100 | 6.14% | 7.36% | 7.14% | 8.56% | 8.14% | 9.76%
4200 | 6.13% | 7.36% | 7.13% | 8.56% | 8.13% | 9.76%
4300 | 6.13% | 7.35% | 7.13% | 8.55% | 8.13% | 9.75%
4400 | 6.12% | 7.34% | 7.12% | 8.54% | 8.12% | 9.74%
4500 | 6.11% | 7.33% | 7.11% | 8.53% | 8.11% | 9.73%
4600 | 6.1% | 7.32% | 7.1% | 8.52% | 8.1% | 9.72%
4700 | 6.05% | 7.26% | 7.05% | 8.46% | 8.05% | 9.66%
4800 | 6.02% | 7.22% | 7.02% | 8.42% | 8.02% | 9.62%
4900 | 6.01% | 7.21% | 7.01% | 8.41% | 8.01% | 9.61%
5000 | 5.95% | 7.14% | 6.95% | 8.34% | 7.95% | 9.54%
6000 | 5.93% | 7.11% | 6.93% | 8.31% | 7.93% | 9.51%
7000 | 5.9% | 7.08% | 6.9% | 8.28% | 7.9% | 9.48%
8000 | 5.88% | 7.05% | 6.88% | 8.25% | 7.88% | 9.45%
9000 | 5.85% | 7.02% | 6.85% | 8.22% | 7.85% | 9.42%
10000 | 5.8% | 6.96% | 6.8% | 8.16% | 7.8% | 9.36%
12000 | 5.8% | 6.96% | 6.78% | 8.13% | 7.6% | 9.12%
14000 | 5.8% | 6.96% | 6.75% | 8.1% | 7.4% | 8.88%
15000 | 5.6% | 6.72% | 6.75% | 8.1% | 7.4% | 8.88%
16000 | 5.6% | 6.72% | 6.73% | 8.07% | 7.2% | 8.64%
18000 | 5.6% | 6.72% | 6.7% | 8.04% | 7.2% | 8.64%
20000 | 5.4% | 6.48% | 6.68% | 8.01% | 7.2% | 8.64%
22000 | 5.4% | 6.48% | 6.65% | 7.98% | 7.2% | 8.64%
24000 | 5.4% | 6.48% | 6.62% | 7.94% | 7.2% | 8.64%
25000 | 5.2% | 6.24% | 6.62% | 7.94% | 7.2% | 8.64%
26000 | 5.2% | 6.24% | 6.6% | 7.92% | 7.2% | 8.64%
30000 | 5.2% | 6.24% | 6.58% | 7.89% | 7.2% | 8.64%
35000 | 5.2% | 6.24% | 6.55% | 7.86% | 7.2% | 8.64%
40000 | 5.2% | 6.24% | 6.5% | 7.8% | 7.2% | 8.64%
60000 | 4.95% | 5.94% | 6.5% | 7.8% | 7.2% | 8.64%
70000 | 4.85% | 5.82% | 6.5% | 7.8% | 7.2% | 8.64%
80000 | 4.75% | 5.7% | 6.5% | 7.8% | 7.2% | 8.64%

## Fee Look Up Table
FOD Fee Lookup Table | Projects with ONLY Local Funds | [7 empty] | Civic Structure | Cost of Construction | Yes / No
| TCC | FOD | [6 empty] | General Contractor | 0 | No
|  | Admin Fee | [6 empty] | 0
| 0 | 0%
| 1 | 2%
| 1000000 | 2%
| 4000000 | 2%
| 20000000 | 2%
1. Fee is charged for amounts in each dollar range.
2. For projects with State funds, FOD admin fee is 1.5%.
CMR Fee Lookup Table | Cost of Construction (At least this much) | CMR General Conditions | CM at Risk Fee | CM Contingency | % Sum | Pre-Con Stage Comp | CMA Fee
0 | 0 | 6.5% | 4.25% | 2.5% | 10.75% | 2.5% | 0%
2500000 | 2287500 | 4.5% | 4% | 2.5% | 8.5% | 2% | 0%
5000000 | 4612500 | 4% | 3.75% | 2.5% | 7.75% | 1.5% | 0%
10000000 | 9325000 | 3.75% | 3% | 2.5% | 6.75% | 1% | 0%
15000000 | 13950000 | 3.5% | 3.5% | 2.5% | 7% | 1% | 0%
20000000 | 18750000 | 3% | 3.25% | 2.5% | 6.25% | 1% | 7.5%
25000000 | 23625000 | 2.5% | 3% | 2.5% | 5.5% | 1% | 7%
50000000 | 47375000 | 2.5% | 2.75% | 2.5% | 5.25% | 1% | 6.5%
75000000 | 71250000 | 2.5% | 2.5% | 2.5% | 5% | 1% | 6%
Design Build Lookup Table | Cost of Construction | DB General Conditions | Construction Stage Design Services | DB Contingency | DB Fee | % Sum | Pre-Con Stage Comp
0 | 0 | 10% | 0% | 3% | 8% | 21% | 2.5%
500000 | 388100 | 9% | 2.88% | 3% | 7.5% | 22.38% | 2.5%
1000000 | 805160 | 8% | 2.484% | 3% | 6% | 19.48% | 2.5%
1500000 | 1238820 | 7% | 2.412% | 3% | 5% | 17.41% | 2.5%
2000000 | 1678200 | 6% | 2.34% | 3% | 4.75% | 16.09% | 2.5%
2500000 | 2155050 | 5% | 2.298% | 3% | 3.5% | 13.8% | 2%
5000000 | 4355400 | 4.5% | 2.142% | 3% | 3.25% | 12.89% | 1.5%
10000000 | 8766200 | 4.25% | 2.088% | 3% | 3% | 12.34% | 1%
15000000 | 13235100 | 4% | 2.016% | 3% | 2.75% | 11.77% | 1%
20000000 | 17861200 | 3.5% | 1.944% | 3% | 2.25% | 10.69% | 1%
25000000 | 22532000 | 3% | 1.872% | 3% | 2% | 9.872% | 1%
50000000 | 45689000 | 2% | 1.872% | 3% | 1.75% | 8.622% | 1%
75000000 | 68815500 | 2% | 1.746% | 3% | 1.5% | 8.246% | 1%
Commissioning Fees Lookup Table | Budget Range | New |  |  | New/ Renovation |  |  | Renovation |  |  | Utility
|  | Low | Avg | High | Low | Avg | High | Low | Avg | High | Low | Avg | High
< | 0 | 0.6686% | 0.7429% | 0.8172% | 0.67% | 0.7429% | 0.82% | 1% | 1.689% | 2.69% | 4.688% | 5.515% | 6.342%
> | 10000000 | 0.6686% | 0.7429% | 0.8172% | 0.67% | 0.7429% | 0.82% | 1% | 1.689% | 2.69% | 4.688% | 5.515% | 6.342%
> | 25000000 | 0.3% | 0.8081% | 1.34% | 0.8428% | 0.9364% | 1.03% | 0.6824% | 0.7583% | 1.31% | 0.3877% | 0.4561% | 0.5245%
> | 50000000 | 0.4% | 0.4853% | 0.57% | 0.4% | 0.4853% | 0.57% | 0.4% | 0.49% | 0.57% | 0.9842% | 1.158% | 1.332%
> | 100000000 | 0.62% | 0.6328% | 0.65% | 0.62% | 0.6328% | 0.65% | 0.3546% | 0.394% | 0.4334% | 1.213% | 1.427% | 1.641%
<= | 100000001 | 0.39% | 0.484% | 0.55% | 0.4918% | 0.5464% | 0.6011% | 0.49% | 0.55% | 0.6% | 1.216% | 1.43% | 1.644%
IDIQ Look Up Table | General Contracting | Design-Build | Design
Barton Malow | 7.5% | 7.5%
Eagle Electrical Services | 8% | 8%
Elford | 8% | 8%
Elite Construction Design Management | 11% | 11%
Premier General Construction | 11% | 11%
Rhoads Construction | 5% | 5%
Roberts Service Group | 9% | 11%
Rockwood Builders | 8% | 10%
Ruscilli Construction Co | 7.5% | 7.5%
Teemok Construction | 5% | 5%
Trimble | 8% | 8%
TBD | 11% | 11%
N/A |  |  | 0%
TBD A/E |  |  | 15%
Advanced Engineering Consultants |  |  | 12%
Barber & Hoffman, Inc. |  |  | 12%
Davis Wince, Ltd. |  |  | 11.5%
DLZ Architecture, Inc. |  |  | 12%
Dynamix Engineering |  |  | 9.5%
Ford & Associates Architects, Inc. |  |  | 12.35%
Garmann/Miller & Associates, Inc. |  |  | 10%
Gunzelman Architecture & Interiors LLC |  |  | 12%
Hasenstab Architects, Inc. |  |  | 15%
Karpinski Engineering |  |  | 13%
LaFontaine Architecture & Design, Inc. |  |  | 12%
Miller/Watson Architects, Ltd. |  |  | 12%
Monks Engineers LLC |  |  | 13.7%
The Osborn Engineering Company |  |  | 7.5%
SHYFT Collective, LLC |  |  | 12%
Star Consultants Inc. |  |  | 11%
The Kleingers Group, Inc. |  |  | 11.5%
Tri-Tech Engineering |  |  | 9%
Van Auken Akins Architects, LLC |  |  | 12%

## Benchmark Cost Per SF
| The information directly to the right provide definitions for construction levels and types displayed in the tables below. The information to the far right is historical data based on completed OSU projects. These numbers are to be used as guides for budget development, the estimator's discretion is required to verify results are suitable for individual projects. | [16 empty] | Benchmark Cost per Square Foot
Definitions & Modifiers
Level of Construction Renovations scope is generally defined as follows:
[19 empty] | New |  |  | Renovation
[10 empty] | Finish | Painting, Carpet/ Flooring, Base, New Lighting on existing circuiting/ clean and/or diffuser improvement NO partition removal/ construction | [7 empty] | COSTS/SF |  |  | COSTS/SF
[19 empty] | LOW | MED | HIGH | LOW | MED | HIGH
[18 empty] | Animal Bed | 155 | 155 | 155 | 155 | 155 | 155
[10 empty] | Light | Painting, Flooring, Ceilings, Door Refinish, light fixture change, diffuser change. Minimal partition rework (80-90% Existing), Minimal casework & MEP changes. | [6 empty] | Athletics | 352 | 352 | 352 | 100 | 100 | 100
[18 empty] | Classroom | 250 | 317 | 370 | 120 | 154 | 200
[18 empty] | Greenhouse | 210 | 210 | 210 | 210 | 210 | 210
[18 empty] | Hangar | 84 | 84 | 84 | 84 | 84 | 84
[10 empty] | Medium | Finishes, minor wall changes (50-70% Existing), minor plumbing changes, new diffusers, new light fixture and branch wiring, new low pressure duct from box to diffuser, fire protection branch pipe & heads for areas due to new walls, Fire alarm wire & devices to match existing. | [6 empty] | Heavy Lab | 300 | 350 | 450 | 240 | 365 | 500
[18 empty] | Hospital | 290 | 431 | 475 | 215 | 274 | 330
[18 empty] | Library | 298 | 298 | 298 | 170 | 199 | 300
[18 empty] | Light Lab | 300 | 312 | 325 | 164 | 211 | 280
[10 empty] | Heavy | Complete demo all walls & ceilings back to structure, all new interior construction, MEP upgrades per space. | [6 empty] | Mechanical | 51 | 51 | 51 | 51 | 51 | 51
[18 empty] | Medium Lab | 300 | 327 | 360 | 190 | 238 | 290
[10 empty] | Modifiers |  | % Add | [5 empty] | Office | 200 | 233 | 330 | 100 | 153 | 200
[10 empty] | 1. | Asbestos Abatement / Hazardous Material Removal | 5% - 10% | [5 empty] | Other | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 2. | Unsuitable Soils Allowance | 3% - 5% | [5 empty] | Parking | 68 | 68 | 68 | 68 | 68 | 68
[10 empty] | 3. | Premium Landscape allowance - above industry standard. | 3% - 5% | [5 empty] | Residence Hall | 180 | 237 | 345 | 127 | 127 | 250
[10 empty] | 4. | Premium for increased sitework / site utilities above typical industry standard. | 3% - 5%
[10 empty] | 5. | Site / Work hour constraints and/or limitations | 0.02
[10 empty] | 6. | Premium for limited renovation size. (less than 5,000 sf) | See Breakdown
| Conceptual Estimate* | [16 empty] | Benchmark Cost per Square Foot (OSU) Backup Projects
Definitions for Space Type
[10 empty] | Classrooms | Student Instruction, inclusive of small seminar rooms, typical classrooms, & lecture halls
| Costs include contractor mark-up | COSTS/SF | [7 empty] | Light Labs | Lab space used for instructional or research purposes requiring specialty equipment that limit its use to specific activities/ functions, but no requiring chemical handling/ storage, fume hoods, or like equipment typically associated with the sciences.
|  | Renovation |  |  |  | New |  |  |  | Medium Lab | Space is used for laboratory research with the need of chemicals, fume hoods and may not require special drains, HVAC, air changes, etc | [6 empty] | Average Costs for New Ground Up Construction Projects in 2013 Dollars | [8 empty] | Average Costs for Remodel Construction Projects in 2013 Dollars
|  | Finish | Light | Med | Heavy | New |  |  |  | Heavy Lab | Space is used for laboratory research with the need of chemicals, fume hoods and requires special drains, HVAC, air changes, electric etc
| General Classroom | 63.745 | 108.68 | 153.615 | 207.955 | 316.635 |  |  |  | Office | Majority of space is dedicated to administration and support of. | [6 empty] | Space Type | Org. Date | TCC | SF |  | Total Construction Costs |  |  | Total Project Costs | Space Type | Org. Date | TCC | SF |  | Total Construction Costs |  | Total Project Costs
| Light labs | 75.24 | 129.58 | 182.875 | 247.665 | 351.12 |  |  |  | Hospital | Space is used for care of patients and can include surgical, diagnostic and pharmaceutical functions
| Medium Labs | 85.69 | 147.345 | 209 | 282.15 | 381.425 |  |  |  | Library | Spaced used for typical library functions such as stacks (book storage), study space reading rooms, & library support services. | [6 empty] | Classrooms |  |  |  | Average | 316.9926 |  |  | 418 | Classrooms |  |  |  | Average | 153.7514 |  | 253.8571
| Heavy Labs | 111.815 | 192.28 | 272.745 | 368.885 | 456.665 |  |  |  | Residence Halls | Student living areas, as well as spaces that support activities of daily living (dining, laundry, support, etc.). | [6 empty] | Example Projects | [8 empty] | Example Projects
| Office | 44.935 | 77.33 | 109.725 | 148.39 | 265.43 |  |  |  | Athletic | Space used by or in support of specific student athletic activities such as indoor playing fields, courts, stadium, locker rooms, ticket sales, etc. | [6 empty] | Fisher College of Bus Ph 1 | 1997 | 57180350 | 172907 | 330.7 |  |  | 459 |  | Stillman Hall Room 100 | 2009 | 400400 | 3040 | 131.7105 |  | 232
| Hospital | 119.13 | 204.82 | 290.51 | 392.92 | 477.565 |  |  |  | Mechanical Space | Rooms containing equipment or supplies associated with the maintenance and operation of a building such as chillers, boilers, IT servers, elevator equipment, etc. | [6 empty] | Fisher College of Bus Ph 2 | 1998 | 58389000 | 159313 | 366.5049 |  |  | 470 |  | Smith Lab learning Space | 2012 | 352000 | 2997 | 117.4508 |  | 214
| Library | 56.43 | 97.185 | 137.94 | 186.01 | 297.825 |  |  |  | Research Greenhouse | Area used for growing, potting, & handling plants & plant materials in support of research activities. | [6 empty] | Knowlton School of Arch | 2002 | 39397959 | 155249 | 253.7727 |  |  | 325 |  | Smith Lab Suite 277 Computer Lab | 2009 | 285000 | 2492 | 114.366 |  | 170
| Residence halls | 44.935 | 76.285 | 108.68 | 146.3 | 263.34 |  |  |  | Animal Bed | Animal Stall Barn Space | [6 empty] | Science Building Quandel | 2012 | 7387200 | 43200 | 171 |  |  | 222.3 |  | Mason Hall | 2011 | 3243150 | 25000 | 129.726 |  | 243
| Athletic | 89.87 | 154.66 | 219.45 | 296.78 | 393.965 |  |  |  | Parking | Areas provided to park vehicles | [6 empty] | Community College Quandel | 2012 | 7572042 | 46741 | 162 |  |  | 210.6 |  | Wexner Education Space | 2012 | 1513724 | 7925 | 191.0062 |  | 301
| Mechanical Space | 36.575 | 62.7 | 88.825 | 120.175 | 240.35 |  |  |  | C/S | Core & Shell Costs | [6 empty] | Liebert Learning Center Quandel | 2012 | 12551040 | 69728 | 180 |  |  | 234 |  | Sinclair Reno Quandel | 2013 |  | 19050 | 201 |  | 261
| Research Greenhouse | 36.575 | 62.7 | 88.825 | 120.175 | 240.35 | [20 empty] | Scripps Renovation Quandel | 2013 |  | 50000 | 191 |  | 356
| Animal Clinic | 70.015 | 119.13 | 169.29 | 228.855 | 334.4
| Metal Building | 27.17 | 47.025 | 66.88 | 89.87 | 130.625
| Hangar |  |  |  |  | 118.085 | [11 empty] | Light Labs |  |  |  | Average | 312.1338 |  |  | 416.5 | Light Labs |  |  |  | Average | 211.4688 |  | 339
| Parking Garage (per space) |  |  |  |  | 20273 | [11 empty] | Example Projects | [8 empty] | Example Projects
| Parking Lot (per space) |  |  |  |  | 5225 | [11 empty] | Parker Food Science | 2000 | 21977416 | 67561 | 325.2974 |  |  | 414 |  | Cunz Hall | 2009 | 16586625 | 58840 | 281.8937 |  | 423
[18 empty] | Psychology Building | 2000 | 39676944 | 132712 | 298.9703 |  |  | 419 |  | James Radiation Oncology | 2013 | 306400 | 1875 | 163.4133 |  | 235
* Costs were increased from version 9 (2016; based on gilbane analysis) by an agreed {FDC Leadership} inflation factor of 4.5%) | [26 empty] | Campbell Hall Rm 213 | 2012 | 180000 | 688 | 261.6279 |  | 363
[27 empty] | Parker Food Science Basement | 2012 | 165000 | 724 | 227.9006 |  | 257
| Scoping* | [7 empty] | Asset Tagging | [17 empty] | Fry Hall Pre Clinic | 2008 | 735050 | 6000 | 122.5083 |  | 417
[15 empty] | Renovation/Small Project |  |  | Medium labs |  |  |  | Average | 327.4211 |  |  | 422.5 | Medium labs |  |  |  | Average | 238.2602 |  | 369.25
|  | COSTS/SF | [6 empty] | Space Type | Description |  | Tag+ | PM++ | Both | Tag+ | PM++ | Both | Example Projects | [8 empty] | Example Projects
[9 empty] | Open Office | General Adminstrative¦ Primarily offices, Typical HVAC Design, Typical office support services |  | 0.2 | 0.08 | 0.28 | 0.22 | 0.088 | 0.308 | Fry Hall Addition | 2005 | 9555000 | 29000 | 329.4828 |  |  | 417 |  | College of Med Addition | 2010 | 8850000 | 36000 | 245.8333 |  | 387
|  | Finish | Light | Med | Heavy | New | <5k sf + |  | Closed Office |  |  | 0.2 | 0.08 | 0.28 | 0.22 | 0.088 | 0.308 | Sisson Hall Replacement | 2000 | 34105000 | 113607 | 300.2016 |  |  | 389 |  | Morehouse 1st Floor lab | 2011 | 820293 | 3546 | 231.3291 |  | 412
| General Classroom | 66.88 | 113.905 | 161.975 | 190.19 | 190.19 | 5% |  | Support Staff |  |  | 0.2 | 0.08 | 0.28 | 0.22 | 0.088 | 0.308 | PT/OT Classroom Building Quandel | 2013 |  |  | 326 |  |  | 424 |  | Bio Sci 3rd floor renovation | 2011 | 2939047 | 4287 | 685.572 |  | 891
| Lecture Hall | 59.565 | 101.365 | 143.165 | 169.29 | 169.29 | 5% |  | Metal Building |  |  | 0.2 | 0.08 | 0.28 | 0.22 | 0.088 | 0.308 | Science Building Quandel | 2013 |  |  | 354 |  |  | 460 |  | Bio Sci 5th & 9th Floor reno | 2009 | 3248185 | 17500 | 185.6106 |  | 254
| Light Wet Lab | 89.87 | 154.66 | 218.405 | 257.07 | 257.07 | 15% |  | General Classroom | General Academic ¦ Primarly Classroom/Offices, Typical HVAC design, typical student support amenities |  | 0.22 | 0.08 | 0.3 | 0.242 | 0.088 | 0.33 | [9 empty] | Jennings Hall Renovation | 2005 | 29942000 | 103153 | 290.2679 |  | 424
| Light Dry Lab | 73.15 | 124.355 | 176.605 | 207.955 | 207.955 | 5% |  | Lecture Hall |  |  | 0.22 | 0.08 | 0.3 | 0.242 | 0.088 | 0.33
| Med Wet Lab | 182.875 | 182.875 | 269.61 | 305.14 | 305.14 | 15% |  | Library |  |  | 0.22 | 0.08 | 0.3 | 0.242 | 0.088 | 0.33 | Heavy labs |  |  |  | Average | 350.0692 |  |  | 463.3333 | Heavy labs |  |  |  | Average | 365.3424 |  | 540.9
| Med Dry Lab | 142.12 | 142.12 | 200.64 | 236.17 | 236.17 | 8% |  | Light Wet Lab | Science/Lab Academic ¦ Primarily lab areas, specialty services, specialty equipment, precision HVAC control, specialty gases/services, typical student support services |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Example Projects | [8 empty] | Example Projects
| Heavy Wet Lab | 129.58 | 222.585 | 315.59 | 370.975 | 370.975 | 15% |  | Light Dry Lab |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Robinson Lab | 2002 | 78924000 | 232306 | 339.7415 |  |  | 446 |  | McPherson Lab Renovation | 1997 | 28891000 | 118513 | 243.7792 |  | 321
| Heavy Dry Lab | 108.68 | 187.055 | 264.385 | 311.41 | 311.41 | 10% |  | Med Wet Lab |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Aronoff Lab | 2001 | 32540000 | 107250 | 303.4033 |  |  | 367 |  | James Linnear Accelerator | 2011 | 420671 | 850 | 494.9071 |  | 807
| Open Office | 37.62 | 63.745 | 90.915 | 106.59 | 106.59 | 5% |  | Med Dry Lab |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Newman Wolfram | 1994 | 21128420 | 62739 | 336.7669 |  |  | 439 |  | UHE Nuclear Med Lab Reno | 2011 | 183484 | 700 | 262.12 |  | 375
| Closed Office | 57.475 | 98.23 | 138.985 | 164.065 | 164.065 | 8% |  | Heavy Wet Lab |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | CBEC | 2014 | 100211000 | 225000 | 445.3822 |  |  | 566 |  | Vet Hosp SAOP | 2013 | 1351000 | 5700 | 237.0175 |  | 337
| Library | 64.79 | 110.77 | 125.4 | 183.92 | 183.92 | 10% |  | Heavy Dry Lab |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Bio Med Research Tower | 2003 | 131529000 | 408037 | 322.3458 |  |  | 430 |  | Col Police Crime Lab Quandel | 2013 |  | 35400 | 339 |  | 440.7
| Residence halls | 51.205 | 88.825 | 125.4 | 147.345 | 147.345 | 15% |  | Research Greenhouse |  |  | 0.3 | 0.15 | 0.45 | 0.33 | 0.165 | 0.495 | Physical Science Research Building | 1998 | 69144000 | 196000 | 352.7755 |  |  | 532
| Athletic | 103.455 | 177.65 | 251.845 | 296.78 | 296.78 | 5% |  | Mechanical Space | Faciities/Infrastructure ¦ Facilities infrastructure buildings (Chilled Water Plant, Powerhouse/CUP, Electrical/Generator, etc) |  | 0.31 | 0.18 | 0.49 | 0.341 | 0.198 | 0.539
| Mechanical Space | 41.8 | 72.105 | 102.41 | 120.175 | 120.175 | 20% |  | Animal Clinic | Medical Facilities ¦ Hospitals, Medical Services/Procedures, special HVAC controls/systems, specialty gases/service, patient support services, etc. |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | Office |  |  |  | Average | 233.3258 |  |  | 296.5 | Office |  |  |  | Average | 153.0704 |  | 224.325
| Research Greenhouse | 41.8 | 72.105 | 102.41 | 120.175 | 161.975 | 0% |  | Patient Room |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | Example Projects | [8 empty] | Example Projects
| Animal Clinic | 80.465 | 136.895 | 194.37 | 228.855 | 221.54 | 0% |  | Surgery |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | 4 - H Center | 2007 | 13139978 | 40287 | 326.1593 |  |  | 388 |  | Journalism Offices | 2011 | 1254000 | 8400 | 149 |  | 291
| Metal Building | 31.35 | 54.34 | 76.285 | 89.87 | 89.87 |  |  | Imaging |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484
| Patient Room | 111.815 | 191.235 | 270.655 | 318.725 | 318.725 | 10% |  | Outpatient & Ambulatory |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | Library Book Depository 1 | 1995 | 5271000 | 26074 | 202.1554 |  |  | 249 |  | Mendenhall A&S office | 2013 | 178650 | 1849 | 96.6198 |  | 107
| Surgery | 122.265 | 219.45 | 297.825 | 350.075 | 350.075 | 20% |  | Outpatient Cancer |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | Library Book Depository 2 | 2001 | 3177000 | 12471 | 254.751 |  |  | 299 |  | Prior Library Offices | 2011 | 964027 | 11800 | 81.6972 |  | 103
| Imaging | 133.76 | 229.9 | 324.995 | 382.47 | 382.47 | 10% |  | Pre/Post OP, Critical Care |  |  | 0.29 | 0.15 | 0.44 | 0.319 | 0.165 | 0.484 | Longaberger Alumni | 1998 | 12541000 | 56705 | 221.1622 |  |  | 307 |  | Lincoln Tower Bio Informatics | 2013 | 2603500 | 24307 | 107.1091 |  | 140
| Outpatient & Ambulatory | 114.95 | 196.46 | 279.015 | 328.13 | 328.13 | 12% |  | Athletic | Athletic Faciities ¦ Sports Venues and training facilities (locker rooms, fitness/strength equipment, therapy equipment, athletic equipment) |  | 0.22 | 0.13 | 0.35 | 0.242 | 0.143 | 0.385 | Younkin Success Center | 1998 | 12976000 | 63801 | 203.3824 |  |  | 255 |  | Goss Lab Room 302 | 2010 | 180000 | 1160 | 155.1724 |  | 205
| Outpatient Cancer | 87.78 | 151.525 | 214.225 | 251.845 | 251.845 | 15% |  | Residence halls | Student Housing ¦ Dorms, Apartments, Living spaces, etc. These can be very different in design and functionality. The cost represents an average of historical and modern designs. |  | 0.15 | 0.05 | 0.2 | 0.165 | 0.055 | 0.22 | Student Academic Services | 2008 | 24120000 | 125400 | 192.3445 |  |  | 281 |  | 910 Building Renovation Quandel |  |  | 37000 | 201 |  | 261.3
| Support Staff | 64.79 | 111.815 | 157.795 | 186.01 | 186.01 | 8%
| Pre/Post OP, Critical Care | 121.22 | 207.955 | 293.645 | 345.895 | 345.895 | 15% | [10 empty] | Hospital |  |  |  | Average | 431.3164 |  |  | 553.3333 | Hospital |  |  |  | Average | 273.6347 |  | 346.525
[10 empty] | + | Tagging Average Cost per Square Foot based on entire/new building projects. Small projects and renovations require 10% increase. | [6 empty] | Example Projects | [8 empty] | Example Projects
* Costs were increased from version 9 (2016; based on gilbane analysis) by an agreed {FDC Leadership} inflation factor of 4.5%) | [9 empty] | ++ | Preventive Maintenance Average Cost per Square Foot to develop/format PM Procedures (wrench turning maintenance steps) and PM Schedules (frequency and timing for auto‐generation of PM Work Orders) | [6 empty] | OSU Critical Care Tower | 2014 | 474065000 | 1080000 | 438.9491 |  |  | 548 |  | Wiseman Hall Addition | 2002 | 11621000 | 42000 | 276.6905 |  | 321
[18 empty] | Ross Heart Hospital | 2003 | 65768000 | 227123 | 289.57 |  |  | 418 |  | Dodd Hall Reno Various Rooms | 2009 | 2016499 | 9105 | 221.4716 |  | 299
| Core and Shell Costs* | [16 empty] | Davis Heart and Lung | 1998 | 34705000 | 133860 | 259.2634 |  |  | 317 |  | UHE 5 West Renovation | 2008 | 2693767 | 10000 | 269.3767 |  | 341
[18 empty] | New Hospital Quandel | 2013 |  |  | 382 |  |  | 497 |  | Morehouse 7th and 8th Floor | 2010 | 2865000 | 22600 | 126.7699 |  | 185
[18 empty] | New Ambulatory Facility Quandel | 2013 |  | 36260 | 473 |  |  | 615 |  | OR Suite Renovations Quandel |  |  |  | 327 |  | 425.1
|  | New | [24 empty] | Clinical Space Renovations Quandel |  |  |  | 145 |  | 188.5
COSTS/SF
| Space Type | Finish | Light | Med | Heavy | [12 empty] | Library |  |  |  | Average | 298 |  |  | 387.4 | Library |  |  |  | Average | 199.2179 |  | 325.45
| General Classroom | 109.725 | 116.6917 | 123.6583 | 130.625 | [12 empty] | Example Projects | [8 empty] | Example Projects
| Lecture Hall | 109.725 | 116.6917 | 123.6583 | 130.625 | [12 empty] | Univ Texas Buena Vista Building |  |  |  | 298 |  |  | 387.4 |  | Mansfield Bromfield Library | 2011 | 1149123 | 23000 | 49.9619 |  | 100
| Light Wet Lab | 125.4 | 132.3667 | 139.3333 | 146.3 | [21 empty] | Science and Eng Library Reno | 2008 | 372704 | 5279 | 70.6013 |  | 235
| Light Dry Lab | 125.4 | 132.3667 | 139.3333 | 146.3 | [21 empty] | Sullivant Hall Reno | 2012 | 22681000 | 128359 | 176.6997 |  | 249
| Med Wet Lab | 125.4 | 132.3667 | 139.3333 | 146.3 | [21 empty] | Thompson Library | 2007 | 70000000 | 299695 | 233.5708 |  | 407
| Med Dry Lab | 125.4 | 132.3667 | 139.3333 | 146.3 | [21 empty] | Lodi Library Quandel | 2013 |  | 5500 | 316 |  | 410.8
| Heavy Wet Lab | 125.4 | 132.3667 | 139.3333 | 146.3 | [21 empty] | Blackmore Library Reno Quandel | 2013 |  | 24833 | 51 |  | 66.3
| Heavy Dry Lab | 125.4 | 132.3667 | 139.3333 | 146.3
| Open Office | 104.5 | 121.9167 | 139.3333 | 156.75 | [12 empty] | Student Life Residence Halls |  |  |  | Average | 236.7547 |  |  | 311.6333 | Student Life Residence Halls |  |  |  | Average | 127 |  | 165.1
| Closed Office | 104.5 | 121.9167 | 139.3333 | 156.75 | [12 empty] | Example Projects | [8 empty] | Example Projects
| Library | 0 | 0 | 0 | 0 | [12 empty] | Grad and Professional Student Housing | 2002 | 40153000 | 219135 | 183.2341 |  |  | 236 |  | McDonald Hall Renovations Quandel |  |  |  | 127 |  | 165.1
| Residence halls | 0 | 0 | 0 | 0 | [12 empty] | Hall Complex | 2010 | 39505000 | 170800 | 231.2939 |  |  | 326
| Athletic | 0 | 0 | 0 | 0 | [12 empty] | Student Apartment Project Quandel | 2013 |  |  | 226 |  |  | 293.8
| Mechanical Space | 0 | 0 | 0 | 0 | [12 empty] | New Residence Hall Quandel | 2013 |  | 75000 | 181 |  |  | 235.3
| Research Greenhouse | 0 | 0 | 0 | 0 | [12 empty] | New MET Residence Hall Quandel | 2013 |  | 78020 | 256 |  |  | 332.8
| Animal Clinic | 0 | 0 | 0 | 0 | [12 empty] | New Res Hall/Dining Facility Quandel | 2013 |  | 45771 | 343 |  |  | 445.9
| Metal Building | 0 | 0 | 0 | 0
| Patient Room | 146.3 | 156.75 | 167.2 | 177.65
| Surgery | 146.3 | 156.75 | 167.2 | 177.65 | [12 empty] | Athletics Projects |  |  |  | Average | 352 |  |  | 475 | Athletics Projects |  |  |  | Average | 100 |  | 148
| Imaging | 146.3 | 156.75 | 167.2 | 177.65 | [12 empty] | Example Projects | [8 empty] | Example Projects
| Outpatient & Ambulatory | 146.3 | 156.75 | 167.2 | 177.65 | [12 empty] | Schott Practice Facility | 2013 | 14076000 | 40000 | 351.9 |  |  | 475 |  | Varsity Tennis Facility | 2008 | 3996000 | 57000 | 70.1053 |  | 72
| Outpatent Cancer | 146.3 | 156.75 | 167.2 | 177.65 | [21 empty] | WHAC Renovation | 2006 | 16943000 | 170270 | 99.5067 |  | 148
| Support Staff | 146.3 | 156.75 | 167.2 | 177.65
| Pre/Post OP, Critical Care | 146.3 | 156.75 | 167.2 | 177.65 | [12 empty] | Mechanical Projects |  |  |  | Average | 51 |  |  | 66.3 | Mechanical Projects |  |  |  | Average | TBD |  | TBD
[18 empty] | Example Projects | [8 empty] | Example Projects
* Costs were increased from version 9 (2016; based on gilbane analysis) by an agreed {FDC Leadership} inflation factor of 4.5%)
[18 empty] | Research Greenhouse |  |  |  | Average | 210 |  |  | 273 | Research Greenhouse |  |  |  | Average | TBD |  | TBD
[18 empty] | Example Projects | [8 empty] | Example Projects
[18 empty] | Animal Bed |  |  |  | Average | 155 |  |  | 201.5 | Animal Bed |  |  |  | Average | TBD |  | TBD
[18 empty] | Example Projects | [8 empty] | Example Projects
[18 empty] | Parking |  |  |  | Average | 68 |  |  | 88.4 | Parking |  |  |  | Average | TBD |  | TBD
[18 empty] | Example Projects | [8 empty] | Example Projects
[18 empty] | Hanger |  |  |  | Average | 84 |  |  | 109.2 | Hanger |  |  |  | Average | TBD |  | TBD
[18 empty] | Example Projects | [8 empty] | Example Projects

## Consultants
Basic Consultants
Structural, mechanical, plumbing, HVAC, electrical, sprinkler, air & water balance, soils engineer, civil,
and landscape are considered to be part of basic fee or reimbursables. Interiors/FF&E are handled
in a separate section.
Consultants to be Added | Fee Increase |  | Comment
Primary Consultants
Veterinary | 0 or 1 | 0% | One is considered as part of difficulty
Medical planner |  |  | factor in fee schedule.
Kitchen | 2 or more | 0.5%
Lab planning
Library
Museum
Theatre
Music
Sports & Recreation
Other
Secondary Consultants
Traffic (Transportation & Parking) | each | 0.25% | Maximum of 1.00%
Materials
Robotics
Historic
LEED
Acoustic/Sound Engineers
Graphics/Photography
Urban Designer
Code Consultant
Legal
Special Lighting Consultant
Fall Protection
Other
Stand-Alone Consultants
Supplemental Specialized Architect |  | 1%
Hazardous Materials Consultant |  | 0.5%